## general_report
SEF Jira
Displaying 21 issues at 25/Aug/15 6:51 PM.
Project | Key | Summary | Issue Type | Priority | Sub-Tasks | Description | Σ Original Estimate | Story Points | Sprint
IFB299 005 | ZERFIV-2 | Manager: View centre rostering | Story | Must Have |  | As a manager I want to see rosters to make sure the center is staffed at all times. Acceptance Criteria: The roster needs to be accessible at all times |  | 2 | Sprint 4
IFB299 005 | ZERFIV-3 | Manager: Roster changes | Story | Must Have |  | As a manager I want to be able to change the roster so that if people need to change days they can Acceptance Criteria: Edit roster event/s Check that all viewer types have updated roster |  | 4 | Sprint 4
IFB299 005 | ZERFIV-4 | Volunteer: Open new job requests | Story | Must Have |  | As a volunteer I would like to be able to open a job request. Acceptance Criteria: Open a request Submit it to the database Open back up from database |  | 4 | Sprint 2
IFB299 005 | ZERFIV-5 | Volunteer: Contact Information | Story | Should Have | ZERFIV-36, ZERFIV-37, ZERFIV-38, ZERFIV-39, ZERFIV-40 | As a volunteer I would like easy access to migrant and contractor contact information. Acceptance Criteria: Searchable area: Client name Client number job number job address | 64800 | 2 | Sprint 1
IFB299 005 | ZERFIV-6 | Volunteer: Staff rosters | Story | Must Have |  | As a volunteer I would like easy access to my roster. Acceptance Criteria: Can see roster in must up to date form |  | 2 | Sprint 4
IFB299 005 | ZERFIV-7 | Volunteer: Daily Tasks | Story | Should Have |  | would like to see all relevant tasks for the day so that I can be productive and get all the worked planned done asap Acceptance Criteria: List of tasks stored and updated as the user finishes with them |  | 8 | Sprint 6
IFB299 005 | ZERFIV-8 | Volunteer: Templates | Story | Must Have |  | As a volunteer I would like to have access to simple templates to quickly fill out forms Acceptance Criteria: |  | 4 | Sprint 3
IFB299 005 | ZERFIV-9 | Volunteer: Access old documents | Story | Could Have |  | As a volunteer I would like access to old documents at any time. Acceptance Criteria: open a document see if all information is stored correctly |  | 4 | Sprint 5
IFB299 005 | ZERFIV-10 | Volunteer: Job status change | Story | Must Have |  | As a volunteer I want to change the status of jobs. Acceptance Criteria: change the status of the job and save it to the database |  | 1 | Sprint 2
IFB299 005 | ZERFIV-11 | Volunteer: View all unactioned requests | Story | Must Have |  | As a volunteer I would like to view all submitted requests and easily see job progress Acceptance Criteria: pull all active requests from the database that I am in charge of |  | 8 | Sprint 5
IFB299 005 | ZERFIV-12 | Migrant: Volunteer contact details | Story | Should Have |  | As a migrant I would like to be able to see volunteers contact details either face to face or via the website so I can get in contact with them if there is a problem Acceptance Criteria: There is a webpage displaying a simple list of volunteer contact details |  | 2 | Sprint 2
IFB299 005 | ZERFIV-13 | Migrant: Status request | Story | Must Have |  | As a migrant I want to be able to check the status of my request visually, so that i know what stage my job is at without reading reports Acceptance Criteria: |  | 1 | Sprint 2
IFB299 005 | ZERFIV-14 | Migrant: Lodge Request Multi-language | Story | Could Have |  | As a migrant I want to be able to lodge a request in my own language, as this would make it easier for myself to go more in depth with the problem. Acceptance Criteria: Migrant is able to change the language of the page by selecting their language from a dropdown list. |  | 2 | Sprint 3
IFB299 005 | ZERFIV-15 | Migrant: Lodge Jobs | Story | Must Have |  | As a migrant I want to be able to make a job request online, so that i don't have to ring a volunteer to start the process Acceptance Criteria: Migrant is able to enter request details into a web form, which will save job details into the database as an unopened job |  | 4 | Sprint 2
IFB299 005 | ZERFIV-16 | Migrant: Account history | Story | Should Have |  | As a migrant I want to have job history stored in my account, this will allow me to potentially call back a good contractor that was understanding last time Acceptance Criteria: Migrant is able to view their job history and contact details of previous contractors |  | 8 | Sprint 3
IFB299 005 | ZERFIV-17 | Migrant: Online Account Creation | Story | Must Have | ZERFIV-23, ZERFIV-25, ZERFIV-26, ZERFIV-27 | As a migrant, I would like to be able to create an account online, this will allow me to keep all of my information regarding my jobs in a centralised location with easy access Acceptance Criteria: Migrant is able to create an account through the GUI online. After creating an account, the user can revisit the website later using account username and password. | 86400 | 4 | Sprint 1
IFB299 005 | ZERFIV-18 | Migrant: Feedback on providers | Story | Must Have |  | As a migrant, I want to be able to leave feedback on a service provider, this way if a service provider is not doing very well in a certain aspect other migrants will know and will not use that service provider Acceptance Criteria: Migrants are encouraged to leave feedback online after the job is complete, and feedback is displayed on service provider page |  | 8 | Sprint 3
IFB299 005 | ZERFIV-19 | Volunteer: Account Creation | Story | Must Have | ZERFIV-32, ZERFIV-33, ZERFIV-34, ZERFIV-35 | Volunteer will be able to create account and easily manage their works online. Acceptance Criteria: volunteer is able to create an account through the GUI online. After creating an account, the user can revisit the website later using account username and password. | 46800 | 2 | Sprint 1
IFB299 005 | ZERFIV-20 | Volunteer: Roster Change Request | Story | Could Have |  | As a volunteer I would like to be able to submit requests to change the roster If I can not do a shift |  | 4 | Sprint 4
IFB299 005 | ZERFIV-21 | All User: Secured log in to customized home page | Story | Must Have | ZERFIV-41, ZERFIV-42, ZERFIV-43, ZERFIV-44, ZERFIV-45, ZERFIV-46 | All user can log in using their credentials (username, password and type). Acceptance Criteria: Successful and user friendly log in. Only valid access will be shown in the home page depending on the account type. | 86400 | 4 | Sprint 1
IFB299 005 | ZERFIV-22 | Migrant : Contact Information | Story | Must Have | ZERFIV-28, ZERFIV-29, ZERFIV-30, ZERFIV-31 | As a migrant user, I want to be able to add and update contact information, so I can be easily contacted when required. Acceptance Criteria: able to change address, contact number, and email. | 46800 | 2 | Sprint 1
Generated at Tue Aug 25 18:51:19 EST 2015 by Luke Kane using JIRA 6.2.7#6265-sha1:91604a8de81892a3e362e0afee505432f29579b0.